## Slide 1: Pace of Delivery Data Engineering

## Slide 2: Pace of Delivery
Bottleneck | New Approach | Time Saved (Baseline – 6 Months)
RM cycle delays | Impact-based RM + pre-approved patterns | 1–2 wks
Principal Tech Lead wait | Virtual Tech Lead for minor calls | 1–2 wks
TPM/BA dependency | Engineers own Jira DoR | 1 wk
Big-bang delivery | Thin slices & parallel work | 3–4 wks
Manual QA | Automated CI testing | 1–2 wks
From months to outcomes — faster, with quality.
Delivery Slicing
Thin vertical slices
Feature flags
Governance That Moves
Impact-based RM
Pre-approved patterns
Distributed Leadership
Virtual Tech Lead
Shared architecture decision
Self-Sufficient Engineers
Jira discipline
Cross-skill BA + QA
Automation & Tooling
Automated CI Test
Cadence & Communication
Weekly demos
No-meeting zones

## Slide 3
Principal Tech Lead
(Guardrails, Patterns,
Cross-Domain Escalation)
Virtual Tech Lead
(Day-to-Day Unblock,
Minor Modelling Decisions)
Engineer
(Self-Sufficient,
Jira DoR, Build & Test)
Discovery
DoR,Acceptance Criteria in Jira
Build Thin Slice
Early Review
Auto Test & Deploy
Demo
Next Slice
Tier 1
0–20% Overrun
Handled within squad
Shift low-priority stories
Tier 2
20–40% Overrun
Surge mode: borrow
engineers from streams / pool
Tier 3
>40% Overrun
Scope pivot: thin slice
or defer enrichment
Tier 4
Extreme case
Exec escalation:
extend timeline or cut scope
Pace of Delivery Model

## Slide 4
Accelerated Plan - Tabular View
Task Name | Duration (days) | Dependency | Parallel Rule | Start Date | End Date | Assigned Sprint
Project Kickoff | 2 |  |  | 09/08/2025 | 10/08/2025 | 1
Requirements | 10 | Project Kickoff |  | 11/08/2025 | 20/08/2025 | 1
Design | 7 | Requirements | Start once core epics signed (Day 5 of Requirements) | 16/08/2025 | 22/08/2025 | 2
Development A | 10 | Design | Design + 2d | 24/08/2025 | 02/09/2025 | 2
Development B1 (thin slice) | 10 | Design | Design + 3d | 25/08/2025 | 03/09/2025 | 2
Integration – Slice 1 (A + B1) | 5 | Dev A & Dev B1 | Start ASAP after both ready | 03/09/2025 | 07/09/2025 | 3
UAT – Wave 1 (A + B1) | 5 | Integration Slice 1 | Staggered UAT | 08/09/2025 | 12/09/2025 | 3
Development B2 (remaining scope) | 10 | Dev B1 | Immediately after B1 | 04/09/2025 | 13/09/2025 | 3
Integration – Slice 2 (A + full B) | 3 | Dev B2 | Short merge/validation | 13/09/2025 | 15/09/2025 | 3
UAT – Wave 2 (full scope) | 4 | Integration Slice 2 | Focused regression + deltas | 16/09/2025 | 19/09/2025 | 4
Release (blue/green switch) | 1 | UAT Wave 2 | Cutover window | 20/09/2025 | 20/09/2025 | 4